# AgrosTech — 3-Year Hiring Plan (FY2027–FY2029)

Data Room · People & Organization · Draft v2 · September 2026

Status of numbers: headcount, cost, and trigger figures below are planning assumptions, not audited actuals. Cost figures are fully-loaded in the raise’s actual currency (US$, per 04-investment-documents/SAFE_TERMS.md), with R$ shown for context at ≈R$5.00/US$1. This plan is deliberately sized against the US$600,000 confirmed in this round — not against the headcount ambitions of a funded agtech scale-up. Where the logic below borrows structure from a larger company’s playbook, the scale has been rebuilt from AgrosTech’s own numbers, not imported.

## 0. A note from the CEO

Written the way I wish someone had written it for me.

When you’re three people and US$600,000, the temptation is to hire for the company you want to be. The discipline that gets you to Series A is the opposite: hire for the next constraint, and never before it. Every role in this plan exists because a specific bottleneck will appear in a specific quarter, and the person is there one quarter earlier — not because a bigger company’s org chart says the role should exist.

Three beliefs shape everything below:

- Hire where humans are irreplaceable, automate everywhere else. A pilot on a farm at dawn, an agronomist defending a number to a bank’s credit desk, a sales conversation that only closes because someone earned trust in person: these are human. Everything else this company already runs on an internal AI-agent operating layer (see 02-team/ORG_DESIGN.md) — strategy support, marketing content, Deal Desk quoting, finance operations. That’s not a future plan, it’s already running with three people. It’s why this plan can stay this lean and still function.

- Our thesis is a hiring thesis. AgrosTech’s own product tagline — “Dado real de cada hectare: o dono decide, o agrônomo prova” (the owner decides, the agronomist proves) — is not marketing copy, it’s an organizational commitment. If the “agrônomo prova” half of that sentence isn’t backed by credible, named agronomic authority, the Passaporte de Crédito Rural is just a well-designed app. Right now that credibility is carried by an advisor — Michelle Souza Vilela, PhD Agronomy, CDT/UnB (see 02-team/ADVISOR_NOTE.md) — not a full-time hire. That’s the correct sequencing for a US$600K seed, not a gap to apologize for. The first full-time agronomic hire is triggered, not scheduled — see Section 5.

- The hardest constraint isn’t sales, it’s trusted, field-verified data. The M1/M2/M3 model stack (Filtro de Área Útil, Radar SAR Anti-Fuga, Protocolo Halo — see 09-product/TECH_STACK_OVERVIEW.md) is the moat, and 40% of this raise goes into building it (“Dados e IA,” per 04-investment-documents/USE_OF_FUNDS.md). A model is only as good as its ground truth. That makes the first engineering hire, not the first sales hire, the highest-leverage use of this capital — and it’s why HIRING_PLAN.md v1 already had this right before this rewrite: CTO first.

## 1. Where we start

|  | Today (Sep 2026) |
| --- | --- |
| Core team | 3 — Amgad Salih (CEO, interim CTO), Diana Dutra (CCO), Lucas Costa (CDO) — see 02-team/TEAM_BIOS.md |
| Advisory bench | 4 — Chaim Finziola (Credix), Gilberto Damasceno (Shamal Aerospace), Michelle Souza Vilela (PhD Agronomy, CDT/UnB), Leonardo Finziola (Qualcomm, IoT LATAM — technical input + warm intros to São Martinho, Speedbird) — see 02-team/ADVISOR_NOTE.md |
| Operating model | Hybrid: AI-agent layer for strategy/marketing/quoting support; humans for field execution, technical sign-off, and relationship-carrying sales — see 02-team/ORG_DESIGN.md |
| Proof asset | Fazenda Buritis (217.12 ha, Buritis/MG) — the benchmark property live in the saas/ product (2D map, 3D digital twin, ScoreCard). [CONFIRM] whether this is the same property as the deck-confirmed “220ha, Minas Gerais, first paid project” (01-company-snapshot/CASE_STUDY.md) — the hectare count and state are close enough that it’s worth a direct founder confirmation before presenting both as separate facts. |
| Product | Passaporte de Crédito Rural (US$0.80/ha/year subscription) + one-off survey services — see 08-gtm-revenue/PRICING_MODEL.md |
| Raise | US$600,000 seed, YC post-money SAFE, 15% at a US$4M cap — see 04-investment-documents/SAFE_TERMS.md |
| Gaps | No dedicated engineering hire (Amgad covers this on interim basis), no full-time agronomist, no ops/compliance lead, no finance lead |

The honest starting constraint: this raise is roughly an order of magnitude smaller than what a company running the headcount curve of a funded agtech scale-up would have in the bank. That’s not a weakness to paper over — it’s the entire reason this plan exists as trigger-based rather than calendar-based hiring. Every hire below has to earn its own keep against a fixed US$600K before a Series A changes the math.

## 2. Two scenarios, not one trajectory

The reference logic this plan is built from assumes a company already past seed, hiring against R$2–15M/year of payroll capacity. AgrosTech is not there yet. Rather than present a single headcount table that implicitly assumes a Series A that hasn’t happened, this plan separates what US$600K actually funds from what a successful Series A would unlock — the same discipline the financial model applies with Bull/Base/Bear (07-financials/FINANCIAL_MODEL.xlsx).

### Scenario A — Seed-funded (what this US$600K actually buys)

| Function | Today | +18mo (end of seed runway) |
| --- | --- | --- |
| Product, Engineering & Data Science | 1 (Amgad, interim) | 3 (dedicated CTO + geospatial/data engineer, Amgad returns to CEO-only) |
| Sales / Institutional BD | 1 (Diana) | 2 (Diana + 1 institutional sales hire) |
| Agronomy & Technical | 0 FTE (1 advisor) | 0–1 FTE — triggered, not scheduled (Section 5) |
| Field / Survey Operations | 1 (Lucas) | 1–2 — contractor/freelance capacity for survey volume, per the founder’s existing per-service model |
| G&A (Finance, Legal, Compliance) | 0 | 0 FTE — covered by the 10% “Integrações Bacen e segurança” allocation as specialist/contractor engagements, not headcount |
| Total core team | 3 | 6–7 |

This maps directly to 04-investment-documents/USE_OF_FUNDS.md’s confirmed split: 40% Dados e IA funds the two engineering hires above; 30% Vendas institucionais funds the institutional sales hire and its travel/BD costs; 20% Operações e reserva funds survey delivery capacity and the runway buffer; 10% Integrações Bacen e segurança funds the compliance/Bacen-integration specialist work as a contracted engagement rather than a headcount line. The bottom-up monthly build in the financial model’s “Budget (Base)” tab already assumes this exact hiring sequence (CTO from M2, data engineer from M4, sales from M5).

Exit criteria for Scenario A: the two things a Series A investor will actually check — (1) the interim-CTO gap closed with a dedicated hire, and (2) at least one of the named pipeline accounts (Coplacana, Thales’ ~30,000 ha, or an advisor-sourced intro such as São Martinho — see 06-customers/SALES_PIPELINE.md) converted to a paying subscription, proving the sales motion doesn’t depend entirely on founder relationships.

### Scenario B — Series-A-gated (the shape of a real scale-up, contingent)

If Series A capital lands on the timeline implied by the deck’s own Base-case revenue curve (US$0.38M → US$1.32M → US$3.50M, 2027–2029 — see the “Scenarios (Deck)” tab in FINANCIAL_MODEL.xlsx), the headcount curve below is the directionally right shape — regional field density, an in-house agronomy bench, an insourced data-processing function, a proper leadership layer. This is explicitly contingent and should never be presented to an investor as funded by the current US$600K raise — doing so would be the kind of internal inconsistency a diligence process catches in minutes (a use-of-funds table that sums to US$600K sitting next to a payroll table that implies millions).

| Function | End FY2027 (post-Series A) | End FY2028 | End FY2029 |
| --- | --- | --- | --- |
| Field Operations (pilots, crew, regional ops) | 4 | 12 | 25 |
| Data Processing & QA | 1 | 4 | 8 |
| Agronomy & Technical | 1 | 3 | 6 |
| Sales (AE, SDR, RevOps) | 4 | 8 | 15 |
| Customer Success | 1 | 3 | 5 |
| Product, Engineering & Data Science | 4 | 8 | 14 |
| Marketing & Brand | 1 | 2 | 3 |
| G&A (Finance, Legal, People, Exec) | 1 | 3 | 6 |
| Total | ~17 | ~43 | ~82 |

This is roughly a third smaller at every stage than a fully-funded agtech scale-up’s headcount curve would be — deliberately, because AgrosTech’s AI-agent operating layer genuinely displaces headcount that a traditional services company would need in marketing ops, quoting, and finance reporting. That’s the real capital-efficiency story to tell investors, not a rounding error.

## 3. FY2027 in detail — “Close the gap, prove the channel”

This is the only year funded by the current raise; everything past it is Scenario B and conditional.

| Quarter | Role | Why now | Funded by |
| --- | --- | --- | --- |
| Q1 ’27 | CTO / Head of Engineering | Closes the interim-CTO gap. Highest-leverage hire in the company — owns the M1/M2/M3 model stack, moves the enrichment pipeline from simulated to live SICAR/SIGEF integration (see 09-product/PRODUCT_OVERVIEW.md) | Dados e IA (40%) |
| Q2 ’27 | Geospatial / Data Engineer | Second engineering hire, not first — a CTO alone can’t both build and ship. Owns the SAR-radar and anomaly-detection pipeline (M2, M3) | Dados e IA (40%) |
| Q2 ’27 | Institutional Sales / BD hire | Converts the named pipeline (Coplacana, Thales, advisor-sourced São Martinho/Speedbird intros) without founder time as the sole bottleneck. Targets banks, cooperatives, and credit desks — the buyer the Resolução CMN 5.267/2025 regulatory driver actually creates urgency for (see 08-gtm-revenue/GTM_STRATEGY.md) | Vendas institucionais (30%) |
| Ongoing | Survey delivery capacity (contractor/freelance, per existing model) | Scales one-off survey revenue alongside the subscription without a fixed headcount commitment before volume justifies one | Operações e reserva (20%) |
| Ongoing | Bacen integration / compliance specialist (contracted, not FTE) | Builds the MCR 2-9 / ICP-Brasil-signed dossier infrastructure — the actual product of the “Integrações Bacen e segurança” line | Integrações Bacen e segurança (10%) |

What’s deliberately NOT in FY2027: a full-time agronomist, a dedicated ops/compliance hire, a marketing hire, a CFO. Each of these is real and each is triggered in Section 5 — they’re withheld here because US$600K doesn’t cover them without starving the two hires that actually protect the technical moat and prove the institutional-sales motion. A Fortune-500 board would ask “what did you cut, and why” — this is the honest answer.

Exit criteria for FY2027: interim-CTO gap closed; the enrichment pipeline live against at least one real registry source, not simulated; at least one named pipeline account converted; institutional-sales motion proven repeatable by a hire other than the founders.

## 4. Leadership hiring order (Series-A-gated, Scenario B)

Once a Series A unlocks Scenario B’s larger build, this is the order — each role unlocks the next constraint, same logic as the reference this plan draws from:

- CTO / Head of Engineering (already hired in Scenario A — carries forward)

- Geospatial / Data Engineer (already hired in Scenario A — carries forward)

- Institutional Sales / BD lead (already hired in Scenario A — carries forward)

- First full-time Agronomist — converts the advisor-carried agronomic credibility (Michelle Souza Vilela) into a named, deliverable-signing employee once deliverable volume justifies it (trigger in Section 5)

- Customer Success lead — first retention owner, once subscriptions exist to retain

- Finance / Controller (→ CFO) — audit-ready books ahead of Series A diligence, unit-economics ownership

- Head of Operations — ANAC/DECEA compliance, survey delivery quality, once insourced-versus-contractor volume crosses the trigger

- Regional Operations Manager #1 — first geographic expansion node

- Head of People — once headcount crosses ~15–20 and ad hoc hiring stops scaling

- Compliance / Legal counsel (in-house) — data licensing, LGPD, aviation regulation, once outside counsel cost exceeds a loaded hire

## 5. Hiring triggers (how AgrosTech avoids over- and under-hiring)

Every hire past the FY2027 core three is released by a trigger, not a calendar date — the same discipline the reference plan uses, rescaled to AgrosTech’s actual metrics:

| Trigger (leading indicator) | Releases |
| --- | --- |
| Hectares under subscription > 70% of current survey-delivery capacity | +1 survey-delivery contractor/crew |
| Deliverables awaiting agronomic sign-off exceed a 2-week queue | First full-time agronomist hire (converts the advisor role, doesn’t abandon it) |
| Named pipeline conversion rate proves repeatable across ≥2 accounts without founder-led closing | +1 additional institutional sales hire |
| Subscription accounts per relationship-owner exceed an agreed ceiling | First Customer Success hire |
| Cash balance (per FINANCIAL_MODEL.xlsx, Budget tab, “Cash balance” row) falls below a 6-month-runway threshold | Freeze all non-critical hiring immediately — this is the single most important trigger in this table for a US$600K raise |
| Series A closes | Scenario B activates; leadership-order hires in Section 4 begin releasing against the new capital base |

## 6. Compensation, equity & retention

- Cash: at or near market for the two engineering hires — Brazil’s remote-sensing/geospatial talent pool is scarce and competitive; underpaying the CTO-adjacent hire is the single most expensive mistake available to a company whose entire moat is the model stack that hire builds. Sales stays variable-heavy, tied to the same margin discipline already built into the Deal Desk logic elsewhere in this repo — no commission structure that rewards volume over the deal quality the subscription model depends on.

- Equity: vesting is already confirmed — 4 years, 1-year cliff, applying to all three founders (see 02-team/VESTING_AND_ESOP.md). Option pool size for early hires is still [CONFIRM] — that decision has to be made before the SAFE closes (see 04-investment-documents/CAP_TABLE.md), not deferred to when the first hire’s offer letter is drafted.

- Retention: for the two engineering hires specifically — technical authorship on the M1/M2/M3 model documentation, and a clear path to “Head of Engineering” title recognition once Scenario B’s leadership layer forms, rather than losing them to a bigger company’s title inflation.

## 7. Sourcing engine

- Geospatial / remote sensing / data engineering: Brazilian remote-first talent pool, with agtech hubs (Piracicaba/ESALQ-USP, Ribeirão Preto, Viçosa/UFV) as recruiting nodes; Embrapa alumni network given the overlap with the Ceres Cubo classification work already in runner/ceres_cubo/.

- Agronomy (when Section 5’s trigger fires): ESALQ/USP, UFV, UFLA, UFU, UFG, UNESP — and directly through the existing CDT/UnB relationship (Michelle Souza Vilela), which is both an advisory channel and, credibly, a sourcing channel for the first full-time agronomic hire.

- Institutional sales: networks adjacent to the confirmed advisor bench — Chaim Finziola’s fintech/credit-infrastructure network (Credix) and Leonardo Finziola’s active introductions (São Martinho, Speedbird) are a warmer sourcing channel for this specific hire than a generic sales-recruiting search.

## 8. Risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Hiring ahead of revenue on a US$600K raise | Trigger-based releases (Section 5); the cash-balance-below-6-months trigger is a hard stop, not a guideline |
| Series A doesn’t materialize on the deck’s implied timeline | Scenario A is designed to function as a standalone, sustainable state — it is not a “burn and hope” plan; Scenario B never gets presented as committed |
| Key-person dependency on the three founders | The two Scenario-A engineering hires exist specifically to close the interim-CTO single-point-of-failure; institutional sales hire exists to prove the motion survives without founder-led closing |
| Agronomic credibility gap before the first full-time hire | Explicitly carried by an advisor (Michelle Souza Vilela) with real credentials, not silently absent — see Section 0, belief 2 |
| Talent competition for scarce geospatial/remote-sensing engineers | Near-market cash plus real technical ownership (M1/M2/M3 authorship) rather than competing purely on salary against better-funded companies |

## 9. What this plan tells an investor

- Capital-discipline, not headcount ambition, is the story at this stage. US$600,000 funds two engineering hires and one institutional sales hire — nothing more — and this plan says so plainly rather than presenting an org chart the raise can’t actually pay for.

- The AI-agent operating layer is real leverage, not a slide. Three people are already running strategy support, marketing, and quoting functions a traditional company would staff separately — that’s why Scenario A’s core-team-of-six-to-seven is a credible operating unit, not an understaffed one.

- The technical moat has a people plan, and it’s funded first. 40% of the raise goes to the two hires that build M1/M2/M3 — that’s not a rounding choice, it’s the plan’s central bet.

- Every hire past the funded three is tied to a trigger and an exit criterion, not a calendar date — the same discipline a much larger, better-funded agtech company would run, applied honestly to a much smaller balance sheet.

AgrosTech — 3-Year Hiring Plan v2.0 | Confidencial | 2026 | Rebuilt from a larger-scale-up reference plan supplied by the founder (2026-09-24) — structure and trigger logic retained, all headcount/cost figures rescaled to the confirmed US$600,000 raise